## gannt
Task,Start Date,End Date,Duration,Percent Complete,Dependencies
Collect Requirements,2024-01-22,2024-02-04,,,
Create Use Case Diagrams,2024-02-11,2024-02-18,,,
Build Activity Diagrams for Each Use Case,2024-02-15,2024-03-09,,Create Use Case Diagrams,
Research User Interface Designs,2024-02-27,2024-03-07,,,
Build Class Diagram,2024-03-01,2024-03-09,,,
Get Customer Approval,2024-03-10,2024-03-11,,Build Activity Diagrams for Each Use Case,
Build Interface,2024-03-12,2024-03-24,,Get Customer Approval,
Link DB to Interface,2024-03-24,2024-04-03,,Build Interface,
Build Business Logic,2024-04-05,2024-04-27,,Link DB to Interface,
Test System,2024-04-27,2024-05-07,,Build Business Logic,
Deliver System,2024-05-08,2024-05-09,,Test System,
Sign-off Meeting,2024-05-09,2024-05-10,,Deliver System,